## Programme Dashboard
FCC PROGRAMME STATUS DASHBOARD — CLEARSTREAM BANKING S.A.
Reporting Date: 16 March 2026 ¦ Programme: Financial Crime Compliance ¦ Prepared by: FCC PMO Team
TOTAL PROJECTS | RED | AMBER | GREEN | COMPLETE
6 | 1 | 3 | 2 | 1
Project ID | Project Name | Owner | Regulation | % Complete | RAG | End Date | Blockers
FCC-001 | DORA ICT Incident Reporting Framework | CRO / IT Risk | DORA Art. 17-23 | 95% | GREEN | 2025-03-31 | None
FCC-002 | AMLA Readiness Programme | Head of Compliance | EU AML Package (AMLA, AMLR, AM | 35% | AMBER | 2026-07-01 | AMLA supervisory guidelines not yet fully publishe
FCC-003 | CSSF AML/CFT Annual Questionnaire 2025 | Compliance PMO | CSSF Regulation 12-02 | 100% | GREEN | 2025-09-30 | None
FCC-004 | Sanctions Screening Tool Upgrade (World-Check One) | Head of FCC Technology | EU Sanctions Regulation / OFAC | 60% | AMBER | 2025-12-31 | UAT defect backlog — 12 open items, 3 critical
FCC-005 | FATF Travel Rule Implementation (R.16) | Head of AML | FATF Recommendation 16 (update | 15% | RED | 2026-06-30 | Resource constraint — lead engineer on leave Q4 20
FCC-006 | KYC Refresh — Tier 1 Clients (HNWI & PEP) | KYC Operations Lead | CSSF 12-02 / AMLD5 Art. 18 | 70% | AMBER | 2025-12-31 | 24 clients unresponsive — escalation in progress

## Project Details
FCC-001 — DORA ICT Incident Reporting Framework
Owner | Regulation | Regulator | Status | RAG | % Complete
CRO / IT Risk | DORA Art. 17-23 | EBA / CSSF | IN PROGRESS | GREEN | 95%
Implementation of ICT incident classification, reporting procedures, and TLPT (Threat-Led Penetration Testing) framework in compliance with DORA requirements effective January 2025.
# | Milestone | Due Date | Done
1 | ICT incident taxonomy defined | 2024-11-30 | ✓ Done
2 | Reporting templates approved by CSSF | 2024-12-31 | ✓ Done
3 | Staff training completed | 2025-02-28 | ✓ Done
4 | First quarterly DORA report filed | 2025-03-31 | ○ Pending
⚠ Blockers: None
FCC-002 — AMLA Readiness Programme
Owner | Regulation | Regulator | Status | RAG | % Complete
Head of Compliance | EU AML Package (AMLA, AMLR, AMLD6) | AMLA / CSSF | IN PROGRESS | AMBER | 35%
Preparation for direct supervision by the new EU Anti-Money Laundering Authority (AMLA, Frankfurt). Includes gap analysis against AMLR requirements, enhanced CDD procedures for high-risk jurisdictions, and data architecture updates for goAML reporting.
# | Milestone | Due Date | Done
1 | AMLR gap analysis complete | 2025-03-31 | ✓ Done
2 | Enhanced CDD procedures drafted | 2025-06-30 | ○ Pending
3 | goAML system integration tested | 2025-09-30 | ○ Pending
4 | AMLA supervisory readiness review | 2026-06-01 | ○ Pending
⚠ Blockers: AMLA supervisory guidelines not yet fully published
FCC-003 — CSSF AML/CFT Annual Questionnaire 2025
Owner | Regulation | Regulator | Status | RAG | % Complete
Compliance PMO | CSSF Regulation 12-02 | CSSF | COMPLETE | GREEN | 100%
Annual AML/CFT questionnaire submission to CSSF covering transaction monitoring effectiveness, KYC/CDD quality, sanctions screening coverage, and governance arrangements.
# | Milestone | Due Date | Done
1 | Data collection from business lines | 2025-07-31 | ✓ Done
2 | Draft questionnaire reviewed by CCO | 2025-08-31 | ✓ Done
3 | Questionnaire submitted to CSSF | 2025-09-30 | ✓ Done
⚠ Blockers: None
FCC-004 — Sanctions Screening Tool Upgrade (World-Check One)
Owner | Regulation | Regulator | Status | RAG | % Complete
Head of FCC Technology | EU Sanctions Regulation / OFAC | CSSF / OFAC / EC | IN PROGRESS | AMBER | 60%
Upgrade from World-Check legacy to World-Check One API with real-time fuzzy name matching, expanded PEP coverage, and automated alert disposition workflow integrated with case management system.
# | Milestone | Due Date | Done
1 | Vendor selection and contract signed | 2025-05-31 | ✓ Done
2 | UAT environment configured | 2025-07-31 | ✓ Done
3 | Parallel run with legacy system | 2025-10-31 | ○ Pending
4 | Production cutover | 2025-12-31 | ○ Pending
⚠ Blockers: UAT defect backlog — 12 open items, 3 critical
FCC-005 — FATF Travel Rule Implementation (R.16)
Owner | Regulation | Regulator | Status | RAG | % Complete
Head of AML | FATF Recommendation 16 (updated June 2025) | FATF / CSSF | IN PROGRESS | RED | 15%
Implementation of updated Travel Rule requirements for cross-border payment data transmission. Requires integration with SWIFT GPI and coordination with correspondent banking network to ensure originator and beneficiary information flows with every payment.
# | Milestone | Due Date | Done
1 | Legal analysis of R.16 update complete | 2025-07-31 | ✓ Done
2 | Technical specification for SWIFT GPI integration | 2025-09-30 | ○ Pending
3 | Correspondent bank outreach programme | 2025-12-31 | ○ Pending
4 | System implementation and testing | 2026-03-31 | ○ Pending
5 | Go-live | 2026-06-30 | ○ Pending
⚠ Blockers: Resource constraint — lead engineer on leave Q4 2025
FCC-006 — KYC Refresh — Tier 1 Clients (HNWI & PEP)
Owner | Regulation | Regulator | Status | RAG | % Complete
KYC Operations Lead | CSSF 12-02 / AMLD5 Art. 18 | CSSF | IN PROGRESS | AMBER | 70%
Periodic KYC refresh for 847 Tier 1 clients including HNWIs, PEPs, and clients in enhanced due diligence jurisdictions. Target: 100% completion by year-end 2025.
# | Milestone | Due Date | Done
1 | Client segmentation complete | 2025-01-31 | ✓ Done
2 | 500 clients refreshed (Q2 target) | 2025-06-30 | ✓ Done
3 | 750 clients refreshed (Q3 target) | 2025-09-30 | ○ Pending
4 | All 847 clients complete | 2025-12-31 | ○ Pending
⚠ Blockers: 24 clients unresponsive — escalation in progress

## Action Log
Action ID | Project | Action | Owner | Due Date | Priority | Status
ACT-001 | FCC-001 | First quarterly DORA report filed | CRO / IT Risk | 2025-03-31 | MEDIUM | OPEN
ACT-002 | FCC-002 | Resolve: AMLA supervisory guidelines not yet fully published | Head of Compliance | 2026-07-01 | MEDIUM | OPEN
ACT-003 | FCC-002 | Enhanced CDD procedures drafted | Head of Compliance | 2025-06-30 | MEDIUM | OPEN
ACT-004 | FCC-002 | goAML system integration tested | Head of Compliance | 2025-09-30 | MEDIUM | OPEN
ACT-005 | FCC-002 | AMLA supervisory readiness review | Head of Compliance | 2026-06-01 | MEDIUM | OPEN
ACT-006 | FCC-004 | Resolve: UAT defect backlog — 12 open items, 3 critical | Head of FCC Technology | 2025-12-31 | MEDIUM | OPEN
ACT-007 | FCC-004 | Parallel run with legacy system | Head of FCC Technology | 2025-10-31 | MEDIUM | OPEN
ACT-008 | FCC-004 | Production cutover | Head of FCC Technology | 2025-12-31 | MEDIUM | OPEN
ACT-009 | FCC-005 | Resolve: Resource constraint — lead engineer on leave Q4 2025 | Head of AML | 2026-06-30 | HIGH | OPEN
ACT-010 | FCC-005 | Technical specification for SWIFT GPI integration | Head of AML | 2025-09-30 | HIGH | OPEN
ACT-011 | FCC-005 | Correspondent bank outreach programme | Head of AML | 2025-12-31 | HIGH | OPEN
ACT-012 | FCC-005 | System implementation and testing | Head of AML | 2026-03-31 | HIGH | OPEN
ACT-013 | FCC-005 | Go-live | Head of AML | 2026-06-30 | HIGH | OPEN
ACT-014 | FCC-006 | Resolve: 24 clients unresponsive — escalation in progress | KYC Operations Lead | 2025-12-31 | MEDIUM | OPEN
ACT-015 | FCC-006 | 750 clients refreshed (Q3 target) | KYC Operations Lead | 2025-09-30 | MEDIUM | OPEN
ACT-016 | FCC-006 | All 847 clients complete | KYC Operations Lead | 2025-12-31 | MEDIUM | OPEN